## Delay Log
The Delay Log
Track every decision bottleneck from Day 1. This becomes your most powerful evidence for structural changes.
From The CISO Crucible by Andy Dyrcz — thecisocrucible.com/fieldguide
Date | Decision Needed | Who I Needed (Approval Chain) | Request Date | Resolution Date | Wait Time (Days) | Business Impact of Delay | Resolution / Outcome | Category | Notes
2025-01-15 | Approve IR vendor contract | Legal → Procurement → CFO | 2025-01-04 | 2025-01-15 |  | No IR capability during Week 2 incident | Emergency sign-off after incident | Vendor/Contract | Used as evidence in Day 30 board deck
2025-01-22 | Deploy MFA to executive accounts | IT Ops → HR (comms) → CEO office | 2025-01-18 | 2025-01-22 |  | Exec accounts remained vulnerable during phishing campaign | Approved after CEO received phishing attempt | Technical/Security | CEO personally championed after near-miss
2025-02-03 | Hire replacement SOC analyst | HR → Finance → VP Eng | 2025-01-20 | 2025-02-03 |  | Team running 24/7 on-call with 2 people instead of 3 | Approved with 60-day hiring timeline | Staffing | Burnout risk — flagged in Day 30 assessment
Categories:
Vendor/Contract ¦ Technical/Security ¦ Staffing ¦ Budget ¦ Policy ¦ Compliance ¦ Cross-Department

## Summary Dashboard
Delay Log — Summary
Auto-calculated metrics from your Delay Log entries
From The CISO Crucible by Andy Dyrcz — thecisocrucible.com/fieldguide
Metric | Value
Total Logged Delays
Average Wait Time (Days)
Longest Wait (Days)
Most Common Category
Tip: Use these numbers in your Day 30 board presentation to justify structural changes.