## SPOF Register
Single Point of Failure Register
If the 'Backup Plan' column is empty, that's your first action item. (Ch 8)
From The CISO Crucible by Andy Dyrcz — thecisocrucible.com/fieldguide
ID | Function / Capability | Person or System | Type | Risk Level | Backup Plan | Backup Owner | Status | Last Tested | Next Review | Notes
SPOF-001 | Malware analysis & reverse engineering | Senior analyst (solo capability) | Human | Critical | Cross-train 2 junior analysts on basic RE | Security Ops Lead | In Progress | Not yet | 2025-03-15 | Only person who can do deep forensics
SPOF-002 | Firewall rule management | Legacy firewall appliance (EOL) | System | High | Migrate to next-gen FW by Q2 | Network Engineer | Planned | N/A | 2025-02-28 | Vendor support ends March 2025
SPOF-003 | Incident response coordination | CISO (sole decision authority) | Human | Critical | Delegate IR authority to Head of Sec Ops | CISO | In Progress | Tabletop Q1 | 2025-04-01 | Must function without CISO present (Ch 21)
SPOF-004 | Customer payment processing | Single payment gateway provider | System | Critical | Establish secondary gateway contract | IT Ops + Finance | Not Started | N/A | 2025-02-15 | Revenue impact: $X/hour downtime
SPOF-005 | Security awareness training | One contractor (part-time) | Human | Medium | Build champion program for distributed training | Security Ops Lead | Planned | N/A | 2025-03-30 | Champion program scales better (Ch 18)

## SPOF Summary
SPOF Summary Dashboard
Quick view of your failure exposure
From The CISO Crucible by Andy Dyrcz — thecisocrucible.com/fieldguide
Metric | Count
Total SPOFs Identified
Critical Risk
High Risk
Medium Risk
Human SPOFs
System SPOFs
No Backup Plan Yet
Not Yet Tested